## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Pinecone API rate limit reached during large vector queries. | Sprint 5 | Mentor | Integration Issue | Added retry mechanism and optimized query batching. | 2025-01-24 | Closed | Ensure query optimization for production scaling.
|  |  | Incorrect vector dimensions causing query mismatches. | Sprint 5 | Mentor | Data Handling | Investigated and corrected vector dimension mismatch in the model. | 2025-01-25 | Closed | Add a validation check for vector dimensions during processing.
|  |  | Sentiment analysis module producing incorrect sentiment labels. | Sprint 4 | Mentor | Algorithm Issue | Adjusted model parameters and retrained on additional data. | 2025-01-24 | Closed | Use a more diverse dataset for training in the next sprint.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others